## Sheet1
Risk Management Plan
ID | Risk Impact | Probabilty of Occurence | Risk Description | Project impact | Risk Area | Risk Response Strategy/ How we mitigated the risk | Who
1 | Medium | High | Our project team is talented and possesses good technical knowledge, but we lack the physical expertise in some aspects of the design. For example, the team is new to accelerometers and motion tracking elements | Lack of expertice will slow down the flow of the project when team memembers are troubleshooting for too long | Schedule Design Software | 1. Attend classes to improve our PM skills 2. Visit online tutorials and videos to acquire necessary skills | Team Members PM
2 | High | High | Many tasks in the project depend on the motion tracking of the clipper working properly and consistently. The accelerometer presents a lot of noise as well as some drift in the raw values of the acceleration. Additionally there is drift velocity associated with the integration process of the acceleration values. | If the Motion tracking takes too long to get right, it leaves less time for other features. If the motion tracker fails, the project is null | Schedule Coding | 1. Suggestion and feedback from technician and TAs through most stages of motion tracking development 2. Having multiple team members working on it collaboratively 3. A low pass filter is used for getting rid of noise and high frequency components presented in the acceleration values 4. A high pass filter is applied after single integration of the acceleration, to the velocity getting rid of constant velocity values that present drift | Team Members
3 | Medium | Medium | Project has a high dependency on quality, so a single poor customer/technician experience can be damaging to the project | Poor first experience from customer/technician could lead to more design implementations to fix user experience | Schedule | 1. Focus on heavy testing and user experience testing 2. Project safety is #1 priority when working with the clipper | Team Members
4 | High | High | In order to make our product unqiue, a phone app was added as a design feature. App development is new and difficult in itself, plus the design relies on the app for storage of data from the hardware components (i.e. movement and position in 3D space) | The app stores the tracking data and provides an interface for customer input. If this fails to function, motion tracking will have to be recorded manually which is unrealistic when the product is on the market | Schedule Software | 1. Beginning app development as soon as possible 2.Beginning software development as early as possible 3. Consistent testing of the app to motion-tracker interface | Team Members
5 | Low | High | Building the prototype in 2nd semester requires that COVID restrictions allow the meeting/movement of team members. The uncertainty of when lockdowns are implemeneted limits the time available for team members to meet up | Fewer in-person meetings means less collaboration in protoype building and testing | Schedule | 1. Minimum 1 virtual group meeting per week for discussion 2. Detailed updates to those unable to attend prototype designing/testing | Team Members
6 | Low | Medium | Earbuds and Clippers are highley complex and rely on communication between eachother in order to make the system function properly | Lack of connections will require more time and coding spent to ensure they track eachother | Schedule Coding Design | 1. rigorous testing 2. early start on design to insure time for iterations | Team Members
7 | Medium | High | 1. Motion of the head when recieving a haircut from the barber is not necessarily the same as the motion of the head when recieving a haircut from the robotic arm. This displaces the reference frame that the clippers are required to be in. 2. The above can be compensated by simply shifting the reference frames each reference frame to an inertial position as each point on the head remains at a constant distance with respect to the earbuds. Though another problem rises from lengths along the neck not being the same when your head is moved to different positions. This can not simply be compensated by a shift in reference frames as the shift will not account for the location of the neck | Testing/implementing the accelerometers and gyroscopes for the proof of concept creates problems in replicating precise tracking movement. | Schedule Design Software | 1. User replicates the movemenets they did during the inital haircut. 2. Software will be implemented such that the the phone displays the location that the user must move their head to. This also takes out the need to shift the reference frames to inertial reference frames, as their head will be in the same location when recieving a haircut from the robotic arm as it was when recieving a haircut from the barber. | The Project Manager
8 | Medium | Low | To make the design as close to market ready as possible, the implementation of a robot arm into the design will make our product unique but will aslo introduce the issue of finding a robot arm, and then integrating our existing design components into a moving mechanical system | Creating a clipper-earbud system also integrated to a free moving robot arm will add more time and resources in prefecting and understnading how the arm moves and how it will affect the customer's experience. The main concern is the introduction of the arm messing up the motion tracking between the clippers and earbuds due to lack of or extra range of motion. Also, the arm would need to be borrowed for a decent amount of time for demos and testing | Schedule Design Software Budget | 1. making the user replicate their head movements for the "2nd cut" will reduce the range of motion required by the robot arm. This allows more emphasis and testing towards the synchronization of the earbuds-clippers system in order to compensate for the forced limitations of the robotic arm. | Team Members